## Dashboard
Project Name | Project X | Status Date | 2015-07-26 | Overall Status | Red
Project Commentary - The project status is red as there too many high risks and issues open.
Schedule
Budget Risks Issues Decision/Actions/Pending

## Data
Task Information |  | Budget Information |  |  | Schedule
Task Type | No. | Month | Planned | Actual | Task | Start | Finish | Duration
On Track | 25 | 2015-01-01 | 35000 | 32000 | Analysis | 2015-02-18 | 2015-04-01 | 42
Delayed | 10 | 2015-02-01 | 25000 | 27000 | Development | 2015-04-01 | 2015-06-01 | 61
Not Started | 45 | 2015-03-01 | 35000 | 39000 | Quality Assurance | 2015-06-02 | 2015-08-02 | 61
|  | 2015-04-01 | 45000 | 52000 | User Acceptance | 2015-08-02 | 2015-10-02 | 61
Risks |  | 2015-05-01 | 48000 | 34000 | Pre Prod | 2015-10-02 | 2015-12-02 | 61
High | 5 | 2015-06-01 | 52000 | 32000 | Prod | 2015-12-02 | 2015-12-07 | 5
Medium | 8 | 2015-07-01 | 32000 |  | Support | 2015-12-07 | 2015-12-25 | 18
Low | 9 | 2015-08-01 | 43000
|  | 2015-09-01 | 56000
Issues |  | 2015-10-01 | 72000
High | 3 | 2015-11-01 | 34000
Medium | 5 | 2015-12-01 | 25000
Low | 2 | Total | 502000 | 216000
Decisions Actions Changes
Decisions Pending | 2
Actions Pending | 5
Change Requests Pending | 3
Project Status
Red
Green
Amber